## Workdays
Using the WORKDAY and NETWORKDAYS
Task Name - Phase 1 | Start Date | Work Days | Work Days (INTL) | Finish Date | UK Holidays (2020)
Define project goals and objectives | 2023-01-01 | 5 | 2023-01-17 | 2023-01-06 | 2023-01-01 | New Year's Day
Gather functional and non-functional requirements | 2023-01-07 | 2 | 2023-01-11 | 2023-01-10 | 2023-04-02 | Good Friday'2 April (Friday): Good Friday
Analyze user needs and expectations | 2023-01-09 | 10 | 2023-02-08 | 2023-01-23 | 2023-04-05 | Easter Monday'5 April (Monday): Easter Monday
Create wireframes to visualize app layout and navigation | 2023-01-11 | 7 | 2023-02-07 | 2023-01-20 | 2023-05-03 | May Day bank holiday'3 May (Monday): May Day bank holiday
Develop prototypes to demonstrate app functionality and user interactions | 2023-01-13 | 3 | 2023-01-24 | 2023-01-18 | 2023-05-31 | Spring Bank Holiday'31 May (Monday): Spring Bank Holiday
Gather feedback from stakeholders and refine designs accordingly | 2023-01-17 | 3 | 2023-01-25 | 2023-01-20 | 2023-08-30 | Summer Bank Holiday (not Scotland)'30 August (Monday): Summer Bank Holiday (not Scotland)
Set up development environment and tools | 2023-01-20 | 8 | 2023-02-15 | 2023-02-01 | 2023-12-25 | Christmas Day'25 December (Saturday): Christmas Day
Write code according to design specifications | 2023-01-23 | 10 | 2023-02-22 | 2023-02-06 | 2023-12-26 | Boxing Day'26 December (Sunday): Boxing Day
Implement features and functionality iteratively | 2023-01-25 | 6 | 2023-02-15 | 2023-02-02 | 2023-12-27 | Christmas Day holiday'27 December (Monday): Christmas Day holiday
Conduct testing throughout the development process | 2023-01-27 | 5 | 2023-02-14 | 2023-02-03 | 2023-12-28 | Boxing Day holiday'28 December (Tuesday): Boxing Day holiday
Task Name | Start Date | End Date | Network Days | Network Days (INTL)
Research | 2023-01-01 | 2023-04-03 | 66 | 65
Book Venue | 2023-01-07 | 2023-01-14 | 5 | 6
Order Wedding Dress | 2023-01-09 | 2023-01-13 | 5 | 4
Order Bridesmaids Dress | 2023-01-11 | 2023-01-15 | 3 | 4
Book Caterer | 2023-01-13 | 2023-01-28 | 11 | 12
Formulas:
Work Days (INTL) = WORKDAY.INTL([Start Date],[Work Days],"1001111")
Work Days (INTL) = NETWORKDAYS([Start Date],[Work Days],G4:G13)
Finish Date = WORKDAY([Start Date],[Work Days],G4:G13)
Finish Date = NETWORKDAYS.INTL([Start Date],[Work Days],2,G4:G13)